## Sheet1
ATOMS / SEP Screen Development Status
Modules | Sub Sections | Status | Remarks | Total | 60
Define Course Components |  |  |  | Completed | 33
| Add Program | 100% |  | Remaining | 27
| Add Faculty | 100% | Change Design and Parameters |  | 5 | Completed next week
| Add Equipment System | 100% | Implementation of New Design is in progress |  | 8 | On Hold
| Add Equipment System Version | 100% |  |  | 8 | Partially completd
| Add JTS | 100% |  |  | 6 | Not started
| Add JTS Tasks | 100%
| Add Work Package | 100%
| Add Work Package Tasks | 100%
| Add Subject | 100%
| Add Chapter | 100%
| Add Topic | 100%
| Add Grade Categories | 100%
| Add Grade Items (Shades) | 100%
| Add Scales (Unsat, Sat) | 100%
| Add Terms (Levels, Semester) | 100%
| Add Eligibility Criteria | 50%
| Add Certificates | 50%
Course Setup
| Create Course | 100%
| Assign Terms | 100% | Parameters changes occurred
| Assign Activities (JTS, Work Package, Subject) | 100%
| Assign Grade Categories | 100%
| Assign Grade Items | 100%
| Assign Certificate | Pending
| Assign Eligibility Criteria | Pending
| Assign Area (Unit, Base, Work Center) | Vary for SEP/AST/TTS | Only for Trainee/Enrollment Trainee
Add Enrollment
| Define Enrollment | 100% | Api's Developments, DB tables,parameters changes and design changes
| Assign Course | 100%
| Assign Faculty/Trade | 100%
| Assign Term | 100%
| Assign JTS | 100%
| Apply Eligibility Criteria | 70%
| Apply Custom Filters (Waivers, Assignments) | 70%
| Assign Instructor | 100%
| Assign Evaluator | 100%
| Assign Base, Unit, Work Center | 100%
Course Execution
| Trainee Profile | 10%
| Mark Attendance | In-Progress | 2022-07-27
| Task Sign Off | 30% | 2022-07-29
| Schedule Evaluations | Pending | 2022-07-29
| Perform Evaluation | Pending | Development will be started after completion of dependant screens.
| Evaluation Sheet Summary | Pending
| Add Endorsements | 100% | 2022-07-19
| Add Migration | Pending | Discussion Required and sample screen
| Add Events (Games, Extra/Co-curricular) | Pending | Mainly, part of other Programs Like TTS
| Calendar Events | In-Progress | 2022-07-27
| Add Rewards | 100% | 2022-07-19
| Add Punishments | 100% | 2022-07-19
| Add Suspend/Relegation | 100% | 2022-07-19
| Add Re-mustering | Pending | Discussion Required
| Trainee Promotion | 100% | 2022-07-19
| Grade Categories & Items | In-Progress | 2022-07-29
| Course Completion | Pending | This is a automated flag of completion of a course.
| Assign Certificate | Pending | Will be completed in the last.
Analysis / Reports
| Base, Unit, Course Wise Progress | Pending
| Trainee Wise Reports | Pending
| Performance/Grade Progress | Pending
| Migration Reports | Pending
| Trickle Enrollment Reports | Pending
| Ongoing/Upcoming Events | Pending
| Various Progress Summaries | Pending